## Slide 1
Monthly Portfolio Health Review
Professional Services — Client Program Portfolio
Reporting Period: June 8 – June 29, 2026 | Prepared for: Executive Sponsor Review

## Slide 2
Portfolio Snapshot
Where the portfolio stands as of the latest reporting week
Chart: 
| Red | Amber | Green
Projects | 1 | 0 | 2
3
Projects in Portfolio
1 (Project Alpha)
Declining This Month
1 (Project Gamma)
Recovering This Month
4 of 12 project-weeks
Weeks w/ Negative Client Sentiment

## Slide 3
Trend Analysis: Direction Matters More Than a Snapshot
RAG trajectory across the last 4 weekly reporting cycles (2 = Green, 1 = Amber, 0 = Red)
Chart: 
| Wk 1 (Jun 8) | Wk 2 (Jun 15) | Wk 3 (Jun 22) | Wk 4 (Jun 29)
Project Alpha | 2 | 2 | 0 | 0
Project Beta | 2 | 2 | 2 | 2
Project Gamma | 1 | 0 | 1 | 2
Project Alpha — Declining
Green for 2 weeks, then dropped to Red and stayed there. A single vendor dependency is now driving schedule, milestone, and blocker risk simultaneously.
Project Beta — Stable
Held Green for all 4 weeks. No portfolio action needed; useful as a delivery-pattern reference for other engagements.
Project Gamma — Recovering
Dipped to Red in week 2 after a resourcing gap, then recovered once an owner was assigned. Model case for fast course-correction.

## Slide 4
Emerging Risks Across the Portfolio
Patterns that would be missed by reviewing each project in isolation
1
Third-Party / Vendor Dependency Risk
Two of three active projects (Alpha, Gamma) hit blockers tied to external parties or unassigned ownership this month. This is a portfolio-level delivery risk, not a one-off — consider a standing vendor/resourcing escalation path rather than per-project firefighting.
2
Overspend Correlates With Schedule Slip
Project Alpha's budget burn climbed to 114% of plan in the same week its schedule turned Red — spend is accelerating to chase a slipping date, which typically front-loads cost without recovering time.
3
Sentiment Is a Leading Indicator, Not a Lagging One
Client sentiment turned negative on Alpha one full week before the schedule/blocker status flipped to Red. Portfolio-wide, treating sentiment dips as an early-warning trigger — not just a symptom — would buy a week of lead time.

## Slide 5
Spotlight: Project Alpha
STATUS: RED
Schedule
Critical milestone(s) late: Vendor API integration, Security review.
Milestones
2 milestones are overdue: Vendor API integration, Security review.
Blockers
Critical blocker(s) open: Vendor API integration blocked - critical - 21 days open.
Budget
Spend is 113% of planned — overspending.
Sentiment
Stakeholder tone is negative but not escalating.
Bottom line for the client conversation
A single vendor's incomplete API documentation has now blocked integration work for 21 days, cascading into a missed security-review milestone and a go-live date that can no longer hold without intervention. This requires executive-to-executive escalation with the vendor, not another internal follow-up.

## Slide 6
Executive Recommendations
Actions for this coming month, in priority order
1
Escalate the Project Alpha vendor blocker this week
Bring the vendor's account executive into a joint call with our steering committee. Every week of delay is now compounding schedule, budget, and client-confidence risk together.
2
Stand up a standing vendor/resourcing risk review
Two of three projects hit external-dependency blockers this month. A monthly cross-project check on vendor commitments and staffing gaps would catch this earlier than per-project reporting does.
3
Treat sentiment dips as an early trigger, not a footnote
On Alpha, negative sentiment preceded the Red status by a full week. Add a rule: two consecutive weeks of negative sentiment auto-triggers a PM check-in, regardless of the numeric RAG score.
4
Use Project Gamma's recovery as the internal playbook
Assigning clear ownership turned Gamma from Red to Green in two weeks. Document this as a fast-recovery pattern for other PMs facing similar resourcing gaps.

## Slide 7
Appendix: How RAG Status Is Determined
Automated weekly scoring across five weighted signals, with escalation overrides
Schedule (25%)
% of tasks past their planned date; any late critical milestone forces Red.
Budget (20%)
Actual vs. planned spend-to-date. Green 90–110%, Amber 70–90% / 110–130%, Red beyond that.
Milestones (25%)
Overdue milestones and those due within 2 weeks flagged at risk.
Blockers (20%)
Count, severity, and age of open blockers; any critical or 14+ day blocker escalates.
Sentiment (10%)
PM/client narrative tone and week-over-week trend, classified automatically.
Missing data is never treated as automatically Green — it is scored Amber and flagged for follow-up. Critical blockers or 2+ overdue milestones override the weighted score and force Red regardless of other signals.
Full methodology: RAG_METHODOLOGY.md | Agent source: /agent | Weekly reports: /outputs/weekly